## Slide 1
Presented by,
Vipul Ballupet Swamy
Consultant for ZeroG
Airline Routing Tool for the Network Data Planners

## Slide 2: Contents
1. Introduction
Project Objective
North Star Tool Concept
Project Constraints
2. Budget Breakdown
3. Project Plan
Asana-based Milestone Matrix
RACI Phase 1
Project Phases
4. Risk Management & Mitigation Measures
5. Conclusion and Next Steps

## Slide 3: Project Objectives
Client Pain Points
    Use multiple spreadsheets for network planning
    Takes days to understand the commercial impact
Effective and intuitive Tool
    Establish transparency on available data, easily integrate new data source
    Take well-informed decisions on adding / cancelling flights
    Optimize overall commercial performance through a unified, centralized and data-driven team approach
Business KPIs
    Revenue per Mile (RPM)
    Available Seat Mile (ASM)
    Gross profit margin = (Bookings per route - Operation cost per route) / Bookings per Route

## Slide 4
North Star Tool Concept
“We aim to Design or Equip the client with the Tool to Improve their Financial Performance (Revenue) to Thrive in the Marketplace with effective Root Planning”
Fleet Data, Operational Cost Data, Airport Data,
Tax Data
Visual Tool to calculate KPI’s like Gross Profit Margin, Load Factor

## Slide 5: Project constraints
Scope Summary | Available Data
Budget: $500K Timeline: 6 Months Framework : SCRUM Resources: Project Manager x1 Data Engineer x1 Data Scientist x2 Business Data Analyst x1 | Fleet data Operational cost data Airport data Tax data IATA data (new Source)
Milestones | Deliverables
Cloud Integration Beta Release Field Testing | Predictive ML based Forecasting Engine Beta version - IAAS Platform Pilot platform with an Intuitive visual - Dashboard

## Slide 6
Project Duration : 6 Months
Start Date: 2. January 2023
End date: 9. June 2023 + Buffer 15 days
Total Sprints: 11sprints
Project Plan: Asana-based Milestone Matrix

## Slide 7: Budget Breakdown

## Slide 8: Responsibility, Accountability, Consulting, Informed - RACI

## Slide 9: Project Phases
Phase 2
1 sprint
Data Analysis: Gathering, Cleaning
Phase 3
3 sprints
Data exploration, Model creation
Staging servers Integration
UX Visualization Development
Concept Validation
ML Based forecasting Engine Implementation
Validation and Verification
Meetings and Events:
Daily scrum meeting - 15 minutes
Sprint planning - 4 hr/sprint
Sprint review - 2 hr/sprint
Sprint Retrospective - 1.5 hr/sprint
Backlog Refinement - 2 hr/Sprint
Artifacts:
Product Backlog
Sprint Backlog
Product Increment
Released product
Project Plan
Product Road Map

## Slide 10: Project Phases
Phase 5
2 sprints
Pilot platform release
Phase 6
2 sprints
Post Release Phase
Field testing
Project Closing
Documentation
Reporting
Feedback
  IaaS Setup on Cloud
  API and Micro-services Integration
  Implementation and Release of Beta version
  Automated data preparation, blending, and analytics
Phase 4
1 sprint

## Slide 11: Risk Management & Mitigation Measures

## Slide 12: Conclusion and Next steps

## Slide 13
Thank you